## week1
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 1 - Jan 16, 2026 (covers week 1-3 of proj sched)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week2
Computer Science 2 Project | Team Members: | Rheian Jay G. Negad
Group Progress Report |  | Elvin Jerald U. Lim
3rd Quarter
Week 2 - Jan 23, 2026 (covers Week 4)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Modified input handling to avoid errors | if int()is used then program crashes if its value is not a number | Completed
Added the option to cancel transaction | user might use the program and they actually don't want to make purchase or change their mind | Completed
STRENGTH
The system no longer crashes when a user enters letters or symbols. It provides an error message instead
The "0 to cancel" logic gives the user an option to cancel their purchase if the change their mind
Balance deduction and sales tracking are still accurate and are now protected by the new validation gate
AREAS FOR DEVELOPMENT
The program currently only handles one customer per run
There is no authentication beyond the Student ID, so anyone who knows a student number can access and spend their balance
All sales and updated balances are lost once the program ends
STRATEGY FOR SUCCESS
We will start working on a loop so that multiple users can use the program consecutively
Research on how to store the sales and updated balances

## week3
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 3 - Jan 30, 2026 (covers week 5)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week4
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 4 - Feb 6, 2026 (covers week 6)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
write at least 2 task
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS