## week1
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 1 - Jan 16, 2026 (covers week 1-3 of proj sched)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week2
Computer Science 2 Project | Team Members: | Rheian Jay G. Negad
Group Progress Report |  | Elvin Jerald U. Lim
3rd Quarter
Week 2 - Jan 23, 2026 (covers Week 4)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Modified input handling to avoid errors | if int()is used then program crashes if its value is not a number | Completed
Added the option to cancel transaction | user might use the program and they actually don't want to make purchase or change their mind | Completed
STRENGTH
The system no longer crashes when a user enters letters or symbols. It provides an error message instead
The "0 to cancel" logic gives the user an option to cancel their purchase if the change their mind
Balance deduction and sales tracking are still accurate and are now protected by the new validation gate
AREAS FOR DEVELOPMENT
The program currently only handles one customer per run
There is no authentication beyond the Student ID, so anyone who knows a student number can access and spend their balance
All sales and updated balances are lost once the program ends
STRATEGY FOR SUCCESS
We will start working on a loop so that multiple users can use the program consecutively
Research on how to store the sales and updated balances

## week3
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 3 - Jan 30, 2026 (covers week 5)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Start using dictionaries | Moved data from lists to dictionaries | Completed
Add bulk orders | found out how to add bulk orders of an item | Completed
Added Kill switch for faculty | We need a way to shutdown when it's closing time | Completed
STRENGTH
Now using dictionary for better storing of data and stuff
made it so one can order multiple of one item
Now canteen faculty can end the program during closing hour
AREAS FOR DEVELOPMENT
still cannot buy multiple items
anyone who sees the code to end the program will be able to end the program, causing inconvenience
STRATEGY FOR SUCCESS
add more loops in the future so that multiple items can be bought
Still don't know what to do for the second area for development
Also, faculty members can skip the line in the canteen so a separate system for faculty members isn't needed, i think

## week4
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 4 - Feb 6, 2026 (covers week 6)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Tray system | Created dictionary that's like a shopping cart | Complete
Add the ability to add and remove multiple items | Developed the ability to add/remove items from the tray | Complete
Added total revenue for the day | Made it so Canteen employee can see the total sales for the day | Complete
STRENGTH
Customers now have trays for multiple items
They can add/remove items as well
AREAS FOR DEVELOPMENT
still no security(to be done in 4th quarter)
STRATEGY FOR SUCCESS
Find more features to add in the 4th quarter and implement it into the code